# Business Plan: Omni Channel Insights — Real-Time Agent Summary Initiative

## Executive Summary

The Omni-Channel Insights initiative will deliver a real-time agent summary system to Salesforce Customer Service agents, providing AI-generated customer interaction summaries within 2 seconds of customer engagement. This capability will enhance agent productivity, improve customer experience consistency, and enable data-driven insights across all customer interaction channels.

Project Code: ck529
Total Timeline: 26 weeks (January 8 - July 4, 2026)
Go-Live: June-July 2026

## Epic Timeline Overview

| Epic | Title | Sprint | # Sprints | Start | End | Key Deliverables |
| --- | --- | --- | --- | --- | --- | --- |
| Epic 1 | Discovery & Architecture | 47.1-47.3 | 3 | Jan 8 | Feb 18 | Requirements, API specs, system design, LLM evaluation, architecture decisions |
| Epic 2 | Platform Foundation | 47.1-47.6 | 6 | Jan 8 | Apr 1 | Deployment infrastructure, data architecture, integration endpoints, CI/CD pipeline |
| Epic 3 | AI & Analytics Implementation | 47.1-47.6 | 6 | Jan 8 | Apr 1 | AI model integration, prompt optimization, analytics database, data pipeline foundation |
| Epic 4 | Quality Assurance | 48.1-48.5 | 5 | Apr 2 | Jul 4 | Load testing, integration testing, BI dashboards, feedback system, performance validation |
| Epic 5 | Production Launch & Enablement | 48.3-48.5 | 3 | Apr 30 | Jul 4 | Production deployment, monitoring, security validation, documentation, team training |
| Epic 6 | Optimization & Continuous Improvement | 48.1-49.6 | 12 | Apr 2 | Sep 16 | Post-production optimization, system tuning, model improvements, cost optimization |

Critical Priority: Epics 1-3 must target completion by April 1, in-time for Integration Testing and Optimization phase.

Total Project Duration: 26 weeks

## Epic Descriptions & Deliverables

### Epic 1: Discovery & Architecture (Jan 8 - Feb 18 | 3 Sprints | 47.1-47.3)

Significance: Establish shared vision, technical foundation, and comprehensive planning for the entire initiative

Scope of Work:

- Comprehensive requirements gathering and stakeholder alignment

- API design and specification

- AI model evaluation, comparison, and selection

- System architecture design and documentation

- Technical feasibility analysis

- Risk assessment and mitigation planning

- Data flow and integration mapping

Deliverables:

- Approved API specifications and integration contracts

- AI model selection criteria and recommendations

- Detailed system architecture documentation

- Feedback system design framework

- Project risk register and mitigation strategies

- Technical feasibility report

- Data architecture design

Business Impact: Ensures all stakeholders align on requirements and approach before major investment; establishes technical foundation to guide all implementation work

### Epic 2: Platform Foundation (Jan 8 - Apr 1 | 6 Sprints | 47.1-47.6)

Significance: Build the foundational infrastructure platform that powers the entire system

Scope of Work:

- System architecture implementation

- Integration with Salesforce platform and Connect

- Database and storage infrastructure setup (DynamoDB, S3)

- API gateway and service layer development

- Deployment automation and CI/CD pipeline

- Network and security infrastructure

- Service orchestration and configuration management

Deliverables:

- Fully operational deployment platform

- Integration endpoints ready for AI model connectivity

- Automated deployment and monitoring capabilities

- Scalable API infrastructure

- Security and access control implementation

- Environment provisioning (dev, staging, production)

Business Impact: Creates the scalable, secure foundation capable of handling agent and customer traffic at enterprise scale

### Epic 3: AI & Analytics Implementation (Jan 8 - Apr 1 | 6 Sprints | 47.1-47.6)

Significance: Implement the core AI logic and establish analytics foundation for insights and optimization

Scope of Work:

AI/ML Capabilities:

- AI model integration and configuration

- Prompt engineering and optimization

- Performance testing and tuning

- Fallback and error handling mechanisms

- Integration with UCDP data sources

Analytics Foundation:

- Analytics database design and deployment

- Data extraction and transformation pipeline setup

- Data quality and deduplication logic

- ETL processes for operational to analytics data flow

- Data schema design for reporting and insights

Deliverables:

- Fully functional summary generation system

- Optimized response times (targeting 2-5 second delivery)

- Intelligent fallback capabilities for reliability

- Performance benchmarking and tuning results

- Centralized analytics database

- Automated data pipeline from operational system to analytics

- Foundation for downstream dashboards and insights

Business Impact: Delivers the core value proposition—instant AI-generated customer summaries for agents—while building the data infrastructure for performance monitoring and continuous improvement

### Epic 4: Quality Assurance (Apr 2 - Jul 4 | 5 Sprints | 48.1-48.5)

Significance: Ensure system meets performance and reliability requirements before production launch

Scope of Work:

- Comprehensive load and stress testing

- Integration testing with Salesforce and other systems

- Model performance benchmarking

- Performance optimization and tuning

- Business intelligence dashboard deployment

- Feedback system implementation and RALF integration

- Production readiness validation

Deliverables:

- Validated performance against all success criteria

- Integration test results with all dependent systems

- Model performance comparison and recommendations

- Production readiness validation report

- Summary Effectiveness dashboard (quality metrics by summary and model)

- Performance Metrics dashboard (latency, availability, cost)

- Natural language query capability for ad-hoc analysis (RALF)

- Feedback collection and analysis system

Business Impact: Confidence that system will meet business requirements and handle production load before launch

### Epic 5: Production Launch & Enablement (Apr 30 - Jul 4 | 3 Sprints | 48.3-48.5)

Significance: Prepare system and organization for production launch

Scope of Work:

- Production infrastructure hardening

- Monitoring, alerting, and observability setup

- Incident response documentation and procedures

- Security validation and compliance review

- Operational team training and enablement

- End-user documentation and support materials

- Phased rollout execution

Deliverables:

- Production-grade infrastructure with redundancy

- Comprehensive monitoring and alerting system

- Incident response runbooks and troubleshooting guides

- Blue-green deployment capability for safe releases

- Trained operations and support teams

- Complete documentation and runbooks

- Successful phased rollout to production

- Feedback mechanisms for ongoing optimization

Business Impact: Minimizes operational risk, ensures rapid incident response, and successfully transitions system to operational status with sustainable support model

### Epic 6: Optimization & Continuous Improvement (Apr 2 - Sep 16 | 12 Sprints | 48.1-49.6)

Significance: Continuously optimize and improve system performance based on real-world production usage

Scope of Work:

- Real-world performance monitoring and analysis

- Production optimization based on actual usage patterns

- Iterative improvements to summary quality and system performance

- Dashboard refinement and enhancement

- Continuous model tuning based on agent feedback

- Cost optimization and resource utilization analysis

- System reliability improvements

- Scaling adjustments based on actual traffic patterns

Deliverables:

- Post-production optimization reports and system enhancements

- Performance tuning recommendations and implementations

- Model improvements based on real feedback data

- Cost optimization recommendations and implementations

- Enhanced dashboards with additional insights

- System reliability improvements and updates

- Continuous improvement documentation

Business Impact: Ensures continuous improvement and optimization based on real-world usage patterns; maximizes ROI through cost optimization and performance tuning

## Critical Path & Prioritization

### Phase 1: Foundation & Implementation (Epics 1-3) — Must Complete by April 1

Target End Date: April 1, 2026 (End of Sprint 47.6)

Epics 1, 2, and 3 form the critical path and must complete on schedule to enable:

- Epic 1 (Discovery & Architecture): Provides requirements, design, and planning foundation for all implementation work

- Epic 2 (Platform Foundation): Delivers infrastructure and integration layer for the entire system

- Epic 3 (AI & Analytics Implementation): Implements core AI capabilities and analytics foundation

All three epics run in parallel with coordinated dependencies:

- Epic 1 front-loads planning (sprints 47.1-47.3) to guide implementation

- Epics 2 and 3 leverage Epic 1 outputs throughout their execution

- System readiness for comprehensive testing phase starting April 2

Why April 1 Deadline is Critical: Any delays beyond this date compress testing, optimization, and deployment timelines, increasing risk of Go-Live delays.

### Phase 2: Quality Assurance (Epic 4) — April-July

Duration: April 2 - July 4, 2026 (Sprints 48.1-48.5)

Epic 4 focuses on comprehensive quality assurance and validation:

- Load testing and performance validation

- Integration testing with dependent systems

- Dashboard and analytics deployment

- Feedback system implementation

- Production readiness validation

### Phase 3: Production Launch (Epic 5) — May-July

Duration: April 30 - July 4, 2026 (Sprints 48.3-48.5)

Final production deployment and team enablement:

- Overlaps with Epic 4 to enable deployment post-validation

- Phased rollout approach minimizes risk

- Knowledge transfer ensures sustainable operations

- Infrastructure hardening and monitoring setup

### Phase 4: Continuous Optimization (Epic 6) — April-September

Duration: April 2 - September 16, 2026 (Sprints 48.1-49.6)

Post-production optimization and system refinement running in parallel with QA and Launch:

- Real-world performance monitoring and analysis

- Iterative system improvements based on production usage

- Model tuning and cost optimization

- Dashboard refinement and enhancement

- Continuous feedback collection and implementation

## Risk Factors & Mitigation Strategies

### Risk 1: Performance Target (≤2 sec.) Achievement

Description: Delivering consistent 2 seconds or less response times across varying network and user load conditions. Low-latency LLMs (~2 seconds) might exhibit low-quality generations.

Mitigation:

- Comprehensive performance testing with realistic load scenarios

- Continuous exploration of optimization techniques throughout Epics 3, 4, and 6

- Fallback mechanisms to ensure reliability even if performance targets are approached

- Performance monitoring to track real-time metrics post-launch

- Use of caching strategies where applicable to reduce latency

- Epic 6 continuous performance tuning based on production metrics

### Risk 2: Data Availability from UCDP

Description: UCDP (customer interaction history) may not have complete interactions or timely data available for comprehensive summary generation. UCDP releases are based on intent; as of January 6, 2026, about 5 intents are available. Initial fine-tuning is limited because of data availability.

Mitigation:

- Epic 1 requirement: Detailed analysis of data availability and gaps

- Graceful degradation: System will generate summaries with available data

- Fallback messaging for incomplete data scenarios: “No interactions found” message

- Coordination with UCDP team to understand data availability timeline and expectations

### Risk 3: System Scalability Under Peak Load

Description: System may experience bottlenecks or throttling during peak usage periods (storm events) leading to degraded performance or outages.

Mitigation:

- Epic 4 load testing with scenarios exceeding projected peak (100-1000+ concurrent requests)

- Auto-scaling infrastructure configured to handle traffic spikes

- Intelligent fallback mechanisms to gracefully degrade rather than fail

- Epic 6 real-time monitoring and alerting for capacity issues post-launch

### Risk 4: Integration Complexity with Salesforce

Description: Integration with Salesforce agent desktop may face unexpected technical or process challenges

Mitigation:

- Propose early integration design around Epics 1-2

- Dedicated integration testing in Epic 4

- Phased rollout in Epic 5 to identify and resolve integration issues with limited user population first

- Rapid feedback loops from pilot agents during phased rollout

### Risk 5: Model Quality & Feedback Acceptance

Description: AI-generated summaries may not meet agent expectations; low feedback scores. No plan for live agents to provide written statements explaining their feedback.

Mitigation:

- Comprehensive AI model evaluation in Epic 1

- Continuous optimization feedback loops in Epic 3

- Model benchmarking and comparison in Epic 4

- Feedback system (Epic 4) to capture quality issues early

- Epic 6 continuous model tuning based on production feedback

- Willingness to switch or blend models based on performance data

- Phased rollout allows course correction before full deployment

### Risk 6: Timeline Slippage on Critical Path (Epics 1-3)

Description: Delays to Epics 1-3 cascade to compress testing and deployment phases

Mitigation:

- Clear prioritization: Epics 1-3 are critical path; all resource conflicts resolved in their favor

- Weekly milestone tracking for Epics 1-3

- Parallel execution: All three epics run concurrently with coordinated dependencies

- Epic 1 front-loads critical planning decisions to unblock Epics 2 and 3

- Contingency planning: Identify activities that could be deferred to post-launch if needed

- Buffer time built into Epic 1 (3 sprints) for thorough planning

### Risk 7: DynamoDB Cost Factor

Description: High read/write costs due to large volume of summary requests

Mitigation:

- Understand UCDP indexing and schema

- Optimize data access patterns to reduce read/write operations

- Explore provisioned throughput vs on-demand pricing models

- Monitor and analyze usage patterns to identify cost-saving opportunities

### Risk 8: EDP Replicated UCDP DynamoDB SLAs

Description: Potential latency or availability issues working with replicated UCDP data

Mitigation:

- Understand SLAs and performance characteristics

- Develop at the beginning using replicated DynamoDB table

- Eventually switch to direct UCDP access as soon as feasible

## Success Criteria & Go-Live Readiness

System will be considered ready for production launch when:

✓ All Epics 1-3 completed on schedule by April 1, 2026
✓ Epic 4 quality assurance testing passes all critical criteria
✓ Performance benchmarks met (targeting ≤2 second response times)
✓ Salesforce and Connect integration validation complete
✓ 99.9% availability baseline demonstrated in staging environment
✓ Business intelligence dashboards operational and validated
✓ Production infrastructure hardened and security validated
✓ Operations teams trained and runbooks complete
✓ Go-live communications plan approved and pilot groups identified

Post-Launch Success (Epic 6):

✓ System stability and performance sustained in production (99.9% availability)
✓ Agent feedback on summary quality actively collected and analyzed
✓ Cost optimization opportunities identified and implemented
✓ Model performance continuously improved based on real-world usage
✓ System scaling and infrastructure optimized for actual traffic patterns

## Next Steps

- Week 1 (Jan 8): Kick off Epic 1 (Discovery & Architecture) activities

- Weekly: Steering committee updates on critical path (Epics 1-3) progress

- April 1: Gate review for Epics 1-3 completion before entering Quality Assurance phase (Epics 4, 5, 6)

- April 2: Parallel kickoff of Epic 4 (Quality Assurance), Epic 5 (Production Launch & Enablement), and Epic 6 (Optimization & Continuous Improvement)

- April 30: Production readiness review before Epic 5 phased Go-Live execution

- June-July: Execute phased Go-Live rollout (Epic 5 completion)

- July-September: Continuous optimization and enhancement (Epic 6 post-production phase)

This business plan is a living document and will be updated regularly as the project progresses and business conditions evolve.